## Sheet1
Annex 3: TSI ITALY: Project GANTT CHART
|  |  | 2025 | [6 empty] | 2026 | [11 empty] | 2027
|  |  | m1 | m2 | m3 | m4 | m5 | m6 | m7 | m8 | m9 | m10 | m11 | m12 | m13 | m14 | m15 | m16 | m17 | m18 | m19 | m20 | m21 | m22 | m23 | m24
Output | Tasks and sub-tasks | Deliverable (if applicable) | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Output – IT 1.1 Sustainability and programme management | 1.1.1 Inception | Inception Report (m5), Project summary and public brief (m5) | bar: 2025-06-01 to 2025-10-01
Finalise detailed project plan and logic (objectives, outputs, milestones, risks). | bar: 2025-06-01 to 2025-09-01
Rapid desk review on workforce planning, governance and regional coordination; consolidate evidence pack | bar: 2025-06-01 to 2025-09-01
Stakeholder mapping (national/regional/APs, agencies, professions, academia, civil society) and influence–interest matrix | bar: 2025-06-01 to 2025-09-01
| Scoping mission (fact-finding, coalition building with SG REFORM, beneficiaries) | Scoping Mission report (m2) | bar: 2025-06-01
| Draft and validate the Inception Report (internal governance, workplans, stakeholder analysis, risk management). | Inceptom report (m5) | bar: 2025-06-01 to 2025-10-01
IT.1.1.2 Set up project Steering Committee and relevant technical advisory groups | bar: 2025-07-01 to 2025-12-01
Approve ToR for SC/MG/TWGs; agree decision rights and cadence | bar: 2025-07-01
Nominate members (MoH, Regions/APs via Interregional Technical Committee, AGENAS, ISS, Department of EU Affairs, Observatory/WHO) | bar: 2025-10-01 to 2025-11-01
Constitute thematic TWGs (covering all framework priority areas (1.2 & 1.3) plus investment (1.4)) with chairs, coordinators (WHO/ProMIS), and secretariats; confirm level of deployment (national/ regional/mixed) | bar: 2025-10-01 to 2025-12-01
Approve TWG workplans (objectives, deliverables, milestones, optional pilots) | bar: 2025-10-01 to 2025-12-01
1.1.3 Stakeholder Engagement | bar: 2025-09-01 to 2027-04-01
Engagement plan (audiences, messages, channels, events) | bar: 2025-10-01 to 2025-11-01
National kick-off and periodic workshops/CoP events; continuous consensus-building with stakeholders | bar: 2025-10-01 to 2027-04-01
| 1.1.4 Development of a sustainability plan | Project report and Sustainability plan (m23) | bar: 2027-01-01 to 2027-05-01
Map institutionalisation pathways (policy, governance, resourcing) for the Framework and the Hub; define handover/ownership | bar: 2027-01-01 to 2027-02-01
Draft and validate Project Sustainability Report with SC | bar: 2027-03-01 to 2027-05-01
Output - IT.1.2: Workforce Reform Framework Development | 1.2.1 Assessment of current procedures, guidelines, frameworks | Baseline review (m9) | bar: 2025-09-01 to 2026-02-01
Common analytical template; collect national/regional documents and formal and informal ways of working | bar: 2025-09-01 to 2025-11-01
TWG-led mapping per area; compile baseline review | bar: 2025-11-01 to 2026-01-01
Identify gaps; define recommendations. | bar: 2025-12-01 to 2026-01-01
Validate baseline review with MG/SC | bar: 2026-02-01
| 1.2.2 Support the design of a Framework for Italian Workforce Reform | Draft framework for workforce reofrm (m12) | bar: 2025-09-01 to 2026-06-01
Agree framework architecture (principles, tools, governance, regional deployment options) | bar: 2025-09-01 to 2025-11-01
Draft policy instruments and technical products per strategic area (e.g., scope-of-practice guidance; digital-skills integration in planning models; ethical recruitment pathways; attractiveness/retention toolkits; micro-credential design) | bar: 2025-11-01 to 2026-03-01
Integrate transversal indicators for monitoring and evaluation and operational guidance for regional uptake | bar: 2025-12-01 to 2026-03-01
Options appraisal for operationalisation and piloting (selection criteria, regions/APs, roles, resourcing) | bar: 2026-02-01 to 2026-04-01
Consolidate and submit Framework (IT.1.2) for SC approval | bar: 2026-02-01 to 2026-05-01
| 1.2.3 Support and technical input to the drafting of the Italian National Plan Towards Global Health | Draft chapters (m12) | bar: 2025-09-01 to 2025-12-01
Technical inputs to Chapter 5 (workforce) and alignment with framework options; drafting and review cycles with MoH | bar: 2025-09-01 to 2025-12-01
| 1.2.4 [OBS] Report on international good practice on workforce reform | Evidence report/policy brief (m6) | bar: 2025-08-01 to 2025-12-01
Draft ToR agreed | bar: 2025-08-01 to 2025-09-01
Desk research, key-informant consultations and synthesis (policy-relevant lessons) | bar: 2025-09-01 to 2025-11-01
Draft, peer review and finalise publishable policy brief | bar: 2025-11-01 to 2025-12-01
Output - IT.1.3: WFR Implementation (initiation of enabling measures for subsequent full-scale implementation of the Italian Workforce Reform) | 1.3.1 Operational design of enabling measures for the Framework | Action plan (m12) | bar: 2026-02-01 to 2026-05-01
Package of enabling measures: translate the Framework’s instruments into operational procedures, templates, guidance, checklists, etc. for early use by Regions/APs (national/regional/mixed, per area) | bar: 2026-02-01 to 2026-05-01
Monitoring, evaluation and learning system for early roll-out | bar: 2026-02-01 to 2026-05-01
Interface with the Italian Health Hub aligning measures with funding instruments | bar: 2026-02-01 to 2026-05-01
| 1.3.2 Launch Event | Launch event (m12) | bar: 2026-05-01
Convene implementers to present the Framework and the enabling measures | bar: 2026-05-01
1.3.3 Early roll-out and learning cycles | bar: 2026-05-01 to 2026-10-01
Initiate enabling measures in Regions/Aps: Regions/APs start using operational procedures, templates with TWG support; optional micro-pilots where maturity justifies testing (not mandatory) | bar: 2026-05-01 to 2026-10-01
Operate learning cycles | bar: 2026-05-01 to 2026-10-01
Produce interim evidence | bar: 2026-05-01 to 2026-10-01
1.3.4 Mobilisation and readiness of thematic Technical Working Groups | bar: 2026-04-01 to 2026-06-01
Review TWG composition, scope, workplans for the enabling measures implementation phase) | bar: 2026-04-01 to 2026-06-01
| 1.3.5 Implementation support and project monitoring, reporting, and evaluation | Quaterly reports on progress (m14, 17, 21) | bar: 2026-04-01 to 2027-03-01
Monitoring, evaluating and learning system in action | bar: 2026-04-01 to 2027-03-01
Adapting programming | bar: 2026-04-01 to 2027-03-01
Peer learning / CoP across Italian regions and with Spain cluster | bar: 2026-04-01 to 2027-03-01
| 1.3.6 Finalisation of sustainability report focused on Framework Implementation | Implementation Learning Report, as part of sustainability Plan (m22) | bar: 2027-01-01 to 2027-03-01
Synthesis of the implementation phase learning; revise national framework (policy instruments, operational guidance, indicator set) | bar: 2027-01-01 to 2027-03-01
1.3.7 Formalisation of regional networks and insitutionalisation | bar: 2027-02-01 to 2027-04-01
| Formalisation of regional networks and insitutionalisation | (report on institutionalisation - link to 1.1.4) (m21) | bar: 2027-02-01 to 2027-04-01
Output - IT.1.4: Development of an Italian Health Hub to align strategic investment in health | 1.3.1 Assessment of current procedures, guidelines, frameworks, options appraisal for establishment of EU funding hub pilot | Action plan (m10) | bar: 2025-10-01 to 2026-03-01
Common analytical template; collect national/regional documents and formal and informal ways of working | bar: 2025-10-01 to 2025-12-01
TWG-led mapping per area; compile baseline review | bar: 2025-12-01 to 2026-02-01
Identify options; define recommendations. | bar: 2026-01-01 to 2026-03-01
1.4.2 [OBS] Report on the existing good practice implementation of projects using funding instruments and blended funding for EU funded projects | bar: 2026-11-01 to 2027-05-01
Develop and agree specificatoin, templates, etc. | bar: 2026-11-01 to 2027-01-01
Desk research, key-informant consultations and synthesis (policy-relevant lessons) | bar: 2026-12-01 to 2027-03-01
| Draft, peer review and report | Report (m10) | bar: 2027-04-01 to 2027-05-01
1.4.3: Operationalisation and institutionalisation of the Italian Health Hub | bar: 2026-03-01 to 2026-12-01
Agree hub architecture (principles, tools, governance, regional deployment options) | bar: 2026-03-01 to 2026-04-01
Nominate members (MoH Dept Workforce, MoH Dept Prog. Regions/APs via Interregional Technical Committee, AGENAS, ISS, Department of EU Affairs, Observatory/WHO) | bar: 2026-03-01 to 2026-04-01
Agree areas of technical focus, funding instruments, and workplans with hub working group(s) | bar: 2026-03-01 to 2026-05-01
Develop bid(s) to EU funding instruments (linked to 1.4.4) | bar: 2026-03-01 to 2026-12-01
| 1.4.4 Delivery of training programmes to build the capacity of Italian Authorities to map suitable funds for workforce reform in Italy and develop bids. | Quaterly reports on progress (m14, 17, 21) | bar: 2026-03-01 to 2027-04-01
Developing scope and content of training course, appointing organisation(s) as requireed | bar: 2026-03-01 to 2026-07-01
Delivery of action learning training programme to hub pilot participants | bar: 2026-07-01 to 2027-02-01
Monitoring and evaluation (linked to 1.4.5) | bar: 2026-07-01 to 2027-02-01
1.4.5 Evaluate pilot and provide recommendations | bar: 2026-09-01 to 2027-04-01
Evaluation of hub pilot and recommendations for improvement and institutionalisation (linked to sustainability report 1.1.4) | bar: 2026-10-01 to 2027-04-01
Output - IT-ES.1.1: Mutual ‘cluster’ learning focused on long-term workforce reform and investment | Mutual ‘cluster’ learning focused on long-term workforce reform and investment | bar: 2025-09-01 to 2027-04-01
| 1.1 Agree scope of cluster learning activities | Cluster scope and purpose document | bar: 2025-09-01 to 2025-11-01
| 1.2 Agree workplan for cluster level activities | High-level cluster workplan | bar: 2025-11-01 to 2026-02-01
1.3 Deliver bilateral capacity development, including peer-learning/study visits, online seminars, and cluster workshops | bar: 2026-02-01 to 2027-03-01
| 1.4 Cluster learning report | Cluster learning report (attendance, satisfaction, etc) | bar: 2027-02-01 to 2027-04-01