## TSI Italy
f |  | Result chain | Indicator | Baseline (May 2025) | Target (May 2027) | Sources and means of verifications | Assumptions
IT | Overall objective (impact) | Strengthen Italy’s capacity to strategic workforce reform through the development of a national framework for workforce reform, improving communication, coordination, and alignment between national, regional, and autonomous authorities. | National Health Workforce Reform Framework adopted and aligned nationally and regionally | No unified national workforce reform framework; workforce planning is fragmented across regions (2025). | Framework for Italian health workforce reform developed and formally adopted by the Ministry of Health with endorsement from all Regions/APs by 2027. | – Official National Workforce Reform Framework document (approved and published) – Government decree(s) or policy(ies) endorsing the framework (with regional agreement) – Meeting minutes / Formal Agreement of State-Regions Conference approving the framework | Political commitment to reform remains strong; inter-regional consensus achieved on framework content; no major governance changes disrupt adoption
|  |  | Multi-sectoral and multi-level coordination mechanism for health workforce governance established (e.g. national Steering Committee with Regions/Aps, involving Health, Labour, Finance and Education/University sectors). | Coordination is ad hoc and fragmented | Coordination mechanism instituted by 2026 (e.g. a national Steering Committee/Coordination Group) and meeting at least quarterly through 2027, with active participation of all members | – Terms of reference establishing the coordination committee – Membership list including national, regional and AP representatives – Meeting minutes and progress reports of the committee | Stakeholders remain engaged and committed to regular meetings; Ministry of Health provides continued support; political stability ensures the committee’s mandate is maintained.
IT | Specific objective (outcome) | IT.1 Build national and regional capacity in Italy to deliver strategic workforce reform and sustainable investment in the health workforce | Italian Health Investment Hub established to coordinate and enhance health workforce funding. | No centralized Health Investment Hub for workforce funding; limited coordination of EU fund utilization for health workforce | Health Investment Hub concept and structure developed by 2026, and pilot Hub operational by 2027 to link workforce reforms with improved access to EU funds. | – Investment Hub proposal/strategy document approved by authorities – Official launch of the Hub – Pilot Hub activity reports and meeting minutes demonstrating coordination of funding | Institutional support from health / finance / EU Affairs authorities for the Hub; continued commitment to integrating diverse funding streams for workforce investments
|  |  | Technical Working Groups (TWGs) on health workforce reform are activated and contributing to policy development. | Not available | Four TWGs (covering key strategic areas of the workforce reform agenda + Investment Hub) formed by late 2025, with regular meetings and at least one set of recommendations or draft policy outputs produced by each TWG by 2026 | – TWG terms of reference and official appointment of members (experts from WHO, Ministry, Regions, ISS, AGENAS, etc.) – Minutes of TWG meetings; lists of participants – TWG reports/recommendations submitted for inclusion in the national reform framework | Availability of relevant experts and regional representatives to participate; TWG recommendations are valued and considered by decision-makers; effective facilitation and support for TWGs (e.g. by project team and WHO).
|  |  | Capacity-building workshops on strategic workforce planning and EU fund use delivered to national and regional officials. | Limited structured training for health workforce planning and EU funding acquisition; capacity gaps at regional level | Training program implemented by 2027, involving participants from all 19 regions + 2 APs (at least 20 officials trained) with post-training evaluations showing improved knowledge (at least 80% participant satisfaction). | – Training materials (workshop agendas, presentations) – Participant attendance records (covering all regions) – Post-training evaluation surveys and capacity-building report (documenting number of trainees, satisfaction and learning outcomes) | Regional staff can be released to attend training; trained officials remain in positions to apply skills; training content is relevant and immediately applicable; ongoing support and resources are available to apply new skills in practice.
IT | Output | IT.1.1: Developing a methodology for delivery focusing on long-term sustainability; through an effective approach to project implementation and a formal sustainability plan. | Internal document: Project Sustainability report | Not available | Available | Project report | Governance mechanisms are effective and partners remain engaged; other outputs are delivered as planned; approach to sustainability is credible
|  |  | Internal documents: Inception report: including outputs of scoping review (IT.1.1.1) detailed stakeholder analysis (IT.1.1.2), governance mechanisms (IT.1.1.4) and detailed work plans | Not available | Available | Project report
|  |  | Public document: Project summary and project public brief | Not available | Available | Project report
IT | Output | IT.1.2: Development of a comprehensive draft Framework for Italian Health Workforce Reform. | Evidence report (publishable as policy brief) on international good practice for building and implementing workforce development & coordination strategies [OBS]. | Not available | Available | Project report | Technical working group is well attended and functional; Framework is developed and adopted by regions; staff are released for training
|  |  | Internal document: Capacity building report: technical content, number of organisations and individuals involved in training and capacity building; evaluation including satisfaction and learning assessment | Not available | Available | Project report
|  |  | Internal Document: Final draft Framework for Italian Workforce Reform | Not available | Available | Project report
|  |  | Internal document: Final drafts of chapters provided to Ministry of Health | Not available | Available | Project report
|  |  | Internal document: Summaries of workshops and meetings with relevant bodies; number of organisations involved and individuals attending participant satisfaction | Not available | Available | Project report
|  |  | Internal document: Baseline review of existing workforce governance procedures, guidelines, frameworks, and informal ways of working in Italy. [WHO] | Not completed | Completed | Project report
IT | Output | IT.1.3: Pilot implementation of the Italian Workforce Reform Framework | Internal document: Draft action plan for pilot phase | Not available | Available | Project report | Regions engage with delivery network/mechanisms; capacity building is effective; engagement is maintained throughout
|  |  | Internal document: Final evaluation of pilot phase and key lessons observed | Not available | Available | Project report
|  |  | Internal document: quarterly/bi-annual monitoring reports from the pilot delivery | Not available | Available | Project report
|  |  | Internal document: Report on formalisation and institutionalisation activities linked to framework delivery (as part of final sustainability report). | Not available | Available | Project report
IT | Output | IT.1.4: Development of an Italian Health Hub to align strategic investment in health | Baseline assessment of current use of EU funding in Italy | Not available | Available | Project report | Technical working group is well attended and functional; Framework is developed and adopted by regions; staff are released for training; Regions engage with delivery network/mechanisms; capacity building is effective; engagement is maintained throughout
|  |  | Report on optimal use of blended funding instruments in workforce reform (OBS) | Not available | Available | Project report
|  |  | Meeting notes and participant feedback from IHH meetings during the project life cycle | Not available | Available | Project report
|  |  | Options appraisal on structure of an Italian Health Hub with recommended approach | Not available | Available | Project report
|  |  | Report on training programmes on mapping and applying for EU funding, including all 20 regions, a minimum of 20 participants; and participant satisfaction and learning. | Not available | Available | Project report
|  |  | Internal document: Project evaluation report and recommendations for formalisation and institutionalisation (as part of final sustainability report) | Not available | Available | Project report
Country |  | Result chain | Indicator | Baseline (May 2025) | Target (May 2027) | Sources and means of verifications | Assumptions
IT-ES | Output | IT-ES.1.1: Development of a cross-country community of practice focused on mutual learning and long-term workforce reform | Community of Practice formally established with governance, membership and annual workplan | No formal community of practice; only ad-hoc exchanges | Community constituted with signed Terms of Reference, at least 25 members across Italy/Spain (MoHs, Regions/APs, AGENAS/Spanish Hub, Nursing bodies, WHO/OBS) | ToR; membership list; approved workplans; meeting calendars. | Political/managerial endorsement by both MoHs; members appointed and retained
|  |  | Regular knowledge-exchange cadence maintained | 0 | at least 4 joint sessions held (min. 2/yr) (peer reviews, study visita, joint webinars) on Investment Hub governance and safe nurse staffing | Agendas, attendance sheets, minutes, recordings, slide decks; reports | Availability of key officials; travel funded; translation/briefing support.
|  |  | COP participant satisfaction and capacity building | Not available | at list 60 participants total; at least 80% report improved knowledge | participant lists; pre/post tests; satisfaction surveys; training reports | Staff availability; content tailored to needs; continuous follow-up support.
Horizontal and cross cutting objective of the Action
CC | Output | CC1.1: A suite of "horizontal" or cross-cutting activities that will foster the exchange of evidence, learning and experience within and across project clusters; create synergies; and expand the pool of countries and practitioners involved, amplifying messages, increasing impact and encouraging continuity across project "generations" | Cluster meeting agenda/schedule in place, meetings delivered | 0 | 1-2 meetings per year per cluster | Project report | Availability and agreement of all national stakeholders
|  |  | Broader meeting agenda/schedule in place and participants invited | 0 | 1-2 meetings over the course of the project | Project report
|  |  | Agreed schedule of issues and evidence inputs for the Community of Practice on Transformation | 0 | at least one low-threshold session quarterly, starting in 2026 | Project report
|  |  | Dissemination materials delivered including webinars (1-3 webinars, standalone or as a series) | 0 | 1-3 webinars | Project report
|  |  | Dissemination materials delivered including a mix of collaborative sessions at key conferences (e.g. at least one session at European Health Forum Gastein 2026/2027 and/or European Public Health Conference 2026/2027) | 0 | 2 | Project report
|  |  | Dissemination materials delivered including a minimum of 3 written outputs in brief formats (a mix of, for example, a Eurohealth Special Issue highlighting country and cluster issues, a policy brief on transformation/implementation issues, and/or (a set of) country or topic-specific fiches) | 0 | 3 | Project report

## TSI Spain
f |  | Result chain | Indicator | Baseline (May 2025) | Target (May 2027) | Sources and means of verifications | Assumptions
ES | Overall objective (impact) | ES 1. Strengthen the resilience and sustainability of the Spanish health system through improved governance of health workforce planning and EU fund coordination. | Increased health systems investments through EU funds | No formal mechanism to monitor total volume or thematic distribution of EU-funded health investments. | At least a 10 % increase in the volume of EU-funded investments explicitly directed to health-system strengthening compared to 2025 baseline | -Post-project evaluation reports - Feedback from MoH and Autonomous Regions | - Political commitment is maintained throughout the project period. - EU funding remains available for health systems development.
|  |  | Improvement in nurse staffing distribution by complexity of care | No systematic approach to allocate or monitor nursing resources according to patient complexity. | Establishment of a national reference framework defining criteria for complexity-based workforce allocation. | -Post-project evaluation reports - National/regional workforce data - Feedback from MoH and Autonomous Regions | Political commitment is maintained throughout the project period.
ES | Specific objective (outcome) | ES.1 Support the Ministry of Health (Spanish Health Hub) to enhance its capacity to manage and optimise strategic health and care investments, including a safe allocation of the workforce. | Existence of an operational Health Investment Hub | Fragmented structures dedicated to coordinating or supporting health-related EU investments. | Health Investment Hub established and fully operational within the Ministry of Health | MoH official documents | Coordination mechanisms are institutionalised.
|  |  | Number of regions engaged in strategic prioritisation | No formal strategic prioritisation with involving regions | At least 10 Autonomous Regions actively engaged in structured strategic prioritisation | Workshop reports | Active participation of Autonomous regions.
|  |  | Percentage of EU health funds | No formal mechanism to monitor total volume or thematic distribution of EU-funded health investments. | At least a 10 % increase in the volume of EU-funded investments explicitly directed to health-system strengthening compared to 2025 baseline | - Final strategic investment plan - Funding allocation reports | EU funding remains available for health systems development.
| Output | ES.1.1 Strengthen the Spanish Health Hub with a consolidated proposal and plan for a way of working between national and autonomous regions to increase their collective capacity to manage and optimize EU health and care investments | Prioritisation framework validated by ≥75% of regions | Prioritisation framework not available | Prioritisation framework validated by ≥75% of regions | Workshop minutes | - There are no delays in mapping or data collection. - Institutional fragmentation does not limits consensus.
|  |  | Network of regional focal points operational | Regional focal points available through Ponencia meetings | Network of Regional Focal Points established with defined Terms of Reference, regular meetings, and a shared guidelines for coordination and exchange | Prioritisation report
|  |  | Coordination plan adopted | Not available | Coordination plan for EU-funded health investments adopted by MoH, regional authorities and other Agencies | Stakeholder network list and ToR
|  |  | Final report disseminated | Not available | Final report available | Final report (baseline, gaps analyses, etc.)
ES | Output | ES.1.2 Training and capacity development for selected personnel | Toolkit developed and disseminated | Not available | Toolkit on EU-funded health investment planning, coordination, and monitoring developed, validated, and disseminated to all national and regional stakeholders | Toolkit and training materials | - Availability of regional staff for training. - Linkage between training content and institutional and operational needs.
|  |  | At least 3 training modules implemented | 0 training modules implemented | At least 3 training modules implemented | Workshop feedback forms
|  |  | ≥80% of participants report increased skills on EU funds tools | Not available | ≥80% of participants report increased skills on EU funds tools | Participant evaluation survey
ES | Output | ES.1.3 Developing a comprehensive patient classification system that categorizes patients by complexity of care to determine the required intensity of care, and considers other factors, such as nursing competencies and settings characteristics (Acute Hospitals, Primary Care, Long-Term Care, and Nursing Homes), to ensure equitable allocation of nursing resources across Spain. | Minimum Data Sets (MDS) agreed | Not available | Minimum Data Sets (MDS) agreed | MDS consensus report | - Data heterogeneity across regions allows Minimium Data sets. - Technical challenges can be solved.
|  |  | DATATHON successfully held | Not available | A DATATHON successfully held | DATATHON report
|  |  | Classification system validated by key stakeholders | Not available | Classification system validated | Final system documentation
ES | Output | ES.1.4 Piloting new comprehensive patient classification system that categorizes patients by complexity of care to determine the required intensity of care, and considers other factors, such as nursing competencies and settings characteristics (Acute Hospitals, Primary Care, Long-Term Care, and Nursing Homes), to ensure equitable allocation of nursing resources across Spain. | 3–6 pilot sites successfully implement the system | Not available | 3–6 pilot sites successfully implement the system | Pilot implementation reports | - Pilot sites supports readiness. - Feedback is representative nationwide. - National-level validation is on time. - Political commitment is maintained throughout the project period.
|  |  | Feedback collected and analysed from all pilot regions | Not available | At least 75% report satisfaction | Feedback analysis
|  |  | Final roadmap validated by the Interterritorial Council | Not available | Final roadmap validated | Final roadmap document
Country |  | Result chain | Indicator | Baseline (May 2025) | Target (May 2027) | Sources and means of verifications | Assumptions
IT-ES | Output | IT-ES.1.1: Development of a cross-country community of practice focused on mutual learning and long-term workforce reform | Community of Practice formally established with governance, membership and annual workplan | No formal community of practice; only ad-hoc exchanges | Community constituted with signed Terms of Reference, at least 25 members across Italy/Spain (MoHs, Regions/APs, AGENAS/Spanish Hub, Nursing bodies, WHO/OBS) | ToR; membership list; approved workplans; meeting calendars. | Political/managerial endorsement by both MoHs; members appointed and retained
|  |  | Regular knowledge-exchange cadence maintained | 0 | at least 4 joint sessions held (min. 2/yr) (peer reviews, study visita, joint webinars) on Investment Hub governance and safe nurse staffing | Agendas, attendance sheets, minutes, recordings, slide decks; reports | Availability of key officials; travel funded; translation/briefing support.
|  |  | COP participant satisfaction and capacity building | Not available | at list 60 participants total; at least 80% report improved knowledge | participant lists; pre/post tests; satisfaction surveys; training reports | Staff availability; content tailored to needs; continuous follow-up support.